## Test Plan
ULT-10511 ¦ Test Plan — Export All Scheduled Jobs Report
Jira Ticket | ULT-10511
Summary | Customer Needs a report of all the Scheduled Jobs
Type | Enhancement / Customer Request
Status | QA Approved
Assignee | Sherif Hamdy
QA Engineer | Vijayakumar Seelam
Date | 2026-03-19
Scope
# | In Scope |  | Out of Scope
1 | Export all scheduled jobs (no date filter) |  | Modifying existing per-day export
2 | Format match with existing export template |  | UI redesign
3 | Background/scheduled report execution |  | Real-time streaming export
4 | Download link / notification when ready |  | Email delivery of report
5 | Empty-state handling (no jobs scheduled)
Test Phases & Entry/Exit Criteria
Phase | Description | Entry Criteria | Exit Criteria | Priority
Functional | Verify all positive/negative scenarios | Feature deployed to QA; test data with 3+ scheduled jobs | All High priority tests pass; no blockers open | High
Format Check | Compare exported file vs reference template | Export feature working | Headers and data match reference exactly | High
Performance | Large dataset background job completes within SLA | 1000+ job records loaded | Export completes without timeout/error | Medium
Security | Access control on export endpoint | Auth module tested | Unauthorised access returns 403 | High

## Test Scenarios
ULT-10511 ¦ Test Scenarios — Export All Scheduled Jobs Report
Scenario ID | Title | Pre-condition | Test Steps | Expected Result | Priority
TS-01 | Export all scheduled jobs | User logged in with export permission | 1. Navigate to Scheduled Jobs page 2. Click 'Export All' 3. Verify trigger | Report generation starts successfully | High
TS-02 | Report format matches reference template | Export triggered | 1. Open downloaded file 2. Compare headers with reference template | Headers and row format match reference exactly | High
TS-03 | Report runs as background job (no timeout) | Large dataset in system | 1. Trigger export 2. Confirm UI stays responsive 3. Wait for completion | Report completes in background; UI stays responsive | High
TS-04 | Report includes all scheduled jobs across all dates | Multiple scheduled jobs across different dates | 1. Note total job count 2. Trigger export 3. Compare row count | Row count matches total scheduled jobs in system | High
TS-05 | Column headers and data alignment are correct | Export file available | 1. Open file 2. Validate each column header 3. Check data mapping | All columns correctly labelled; data is aligned | Medium
TS-06 | Downloaded file is accessible after job completes | Background job finished | 1. Click download link 2. Open file | File downloads and opens successfully | Medium
TS-07 | Empty state — no scheduled jobs | No scheduled jobs in system | 1. Trigger export | Empty file generated; no error shown | Medium
TS-08 | Large dataset export completes without error | 1000+ scheduled job records | 1. Trigger export 2. Wait for completion 3. Verify file | Export succeeds with all records present | Medium
TS-09 | Unauthorised user cannot trigger export | User without export permission logged in | 1. Navigate to export page 2. Attempt to trigger export | Access denied; appropriate error message displayed | High
TS-10 | Export is idempotent | Scheduled jobs data unchanged | 1. Run export 2. Run export again 3. Compare files | Both files contain identical data | Low

## Test Cases
ULT-10511 ¦ Test Cases — Export All Scheduled Jobs Report
TC ID | Scenario Ref | Test Case Title | Pre-condition | Test Steps | Expected Result | Priority | Status
TC-01 | TS-01 | Export All button visible to authorised user | User logged in with export permission | 1. Log in as authorised user 2. Navigate to Scheduled Jobs page 3. Check for 'Export All' button | 'Export All' button is visible and enabled | High | Not Run
TC-02 | TS-01 | Clicking Export All triggers background job | User on Scheduled Jobs page | 1. Click 'Export All' 2. Check for confirmation message | Confirmation 'report is being generated' displayed | High | Not Run
TC-03 | TS-02 | Exported file has correct column headers | Export triggered and completed | 1. Download exported file 2. Open file 3. Verify column headers | Headers match: Job Number, Part Number, Description, Quantity, Due Date, Remaining Hours | High | Not Run
TC-04 | TS-04 | Export row count matches total scheduled jobs | Scheduled jobs exist in system | 1. Note total job count in UI 2. Trigger export 3. Open file 4. Count rows | File row count equals total scheduled jobs count | High | Not Run
TC-05 | TS-07 | Empty state — export with no scheduled jobs | No scheduled jobs in system | 1. Navigate to Scheduled Jobs page 2. Click 'Export All' | File with headers only generated; no error message | Medium | Not Run
TC-06 | TS-09 | Unauthorised user is blocked from export | Read-only user logged in | 1. Log in as read-only user 2. Navigate to export endpoint | HTTP 403 or 'Access Denied' message shown | High | Not Run
TC-07 | TS-03 | UI remains responsive during background export | Export triggered | 1. Trigger export 2. Click navigation link while export runs | Navigation link is enabled; page does not freeze | High | Not Run
TC-08 | TS-10 | Export produces identical results on repeated runs | Scheduled job data unchanged between runs | 1. Run export 2. Record status 3. Run export again 4. Compare statuses | Both runs show status 'Completed' or 'Ready' | Low | Not Run